## Slide 1
LESSONS LEARNT
From Deep Ocean Days
to Digital
Lunch & Learn — How we capture, analyse and act on
17 years of project intelligence
Jordan Beaton · Enshore Subsea · 2026
2,990
Lessons Learnt
67
Projects
Notes: Cover slide. Welcome everyone. Today we're talking about lessons learnt — not the filing cabinet version, but 17 years of project intelligence now in one searchable, filterable system.

## Slide 2
2 / 19
AGENDA
Today's
session
01
The Challenge
Why the old way wasn't working
02
The Database
2,990 lessons — what's actually in there
03
Trend Analysis
Patterns across 17 years & 67 projects
04
The New System
IMS Lessons Learnt — how it works
05
Before vs After
Excel vs the new platform
06
Live Demo
See it in action
07
What's Next
Roadmap and how you can contribute
Notes: Walk through the agenda briefly. Emphasise that this is a two-way session — we want people to start thinking about contributing their own lessons.

## Slide 3
3 / 19
📁
The Challenge
How did we manage lessons learnt before?

## Slide 4
4 / 19
The Old Way: 10 Spreadsheets, Zero Visibility
From 2009 to 2026, lessons learnt lived in isolated project files — never connected, rarely actioned.
A B C D E F
LL1 J7177 North Bardawill Failure Low Delivery of 3rd party items...
LL2 J7177 North Bardawill Failure Med Document issue on vessel...
LL3 J9022 Ensign Success Low CTC logistics improved...
LL4 J9099 Bard Failure High Survey equipment delay...
... ... ... ... ... (2,985 more rows across 10 files)
🔍
No search
Need to open every file manually to find a relevant lesson
🔗
No links
Actions raised — never tracked. Who did what? No one knows.
📊
No analysis
Trend analysis means 10 pivots in 10 different Excel files
🔒
No control
10 versions of the 'master' — which one is actually current?
📤
No sharing
Offshore teams couldn't access it. Knowledge stayed onshore.
❌
No action loop
Lessons noted. Lessons filed. Rarely acted on. Repeated.
Notes: The core problem: lessons learnt existed in isolation. Nobody could see across projects. The Deep Ocean → Enshore transition made this worse — files ended up in different places with different formats.

## Slide 5
5 / 19
What's Actually in the Database?
10 source files. One standard layout. Every lesson, every project, back to 2009.
2,990
Total Lessons
Learnt
67
Distinct
Projects
17
Years of
Data
10
Source
Files
📅 Date Range
2009 – 2026 (Deep Ocean days through to today)
⭐ Top Project
Inch Cape — 420 individual lessons
🏭 Top Source
Projects department — 1,476 entries (49% of total)
⚠️ Status
78% logged as Failures / Observations · 10% as Successes
Notes: Let this land. 2,990 lessons across 67 projects — this is a significant body of knowledge that Enshore has never had in one place before.

## Slide 6
6 / 19
📈
Trend Analysis
What patterns emerge when you look at 17 years of data?

## Slide 7
7 / 19
Lessons Learnt by Year
Volume peaks in active offshore installation years. 2026 reflects new IMS data-entry drive.
Chart: 
| 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2023 | 2024 | 2025 | 2026
Lessons | 79 | 153 | 332 | 230 | 332 | 305 | 78 | 43 | 136 | 321 | 100 | 1 | 13 | 28 | 440
2026: New IMS
data entry drive
Notes: Key story: the 2011-2014 peak reflects the big offshore wind installation years. 2016-2017 dip = quieter period. 2026 spike = we're actively entering historical data into the new system. More to come.

## Slide 8
8 / 19
Where Do Lessons Come From?
By originating department — Projects dominates, reflecting offshore installation work volumes.
Chart: 
| Projects | Operations | Engineering | Mobilisation | Project Eng. | Planning | HSEQ
Count | 1476 | 304 | 158 | 134 | 123 | 111 | 55
49%
of all lessons
come from the
Projects team
Engineering, HSE, Mobilisation
and Planning make up
a further 19%
HSE underrepresented —
opportunity to improve
reporting culture
Notes: The big insight here is HSE is significantly underrepresented at only 55 entries out of 2,990. HSE incidents and near-misses rarely become formal lessons. That's a gap we need to close.

## Slide 9
9 / 19
When Do Things Go Wrong?
Operational Issues accounts for 27% of all lessons — the largest single category.
Chart: 
| Operational Issues | Mobilisation | Planning | Trenching | Cable Splice | Trencher Mob.
Count | 811 | 451 | 336 | 130 | 63 | 53
Top 3
stages =
53%
of all lessons
Ops Issues = live site
unpredictability
Mobilisation = where
planning meets reality
Planning = assumptions
that don't survive contact
Notes: Operational Issues + Mobilisation + Planning = more than half of everything we've ever logged. This isn't surprising but it does tell us where to focus pre-project planning and SOP reviews.

## Slide 10
10 / 19
Criticality & Status Split
Of the 2,990 lessons, 580 have unknown criticality — a data quality issue to fix in the new system.
Chart: 
| Medium | Low | High | Critical
Criticality | 992 | 735 | 673 | 8
Status of Known Records
Failure / Observation
78%
Success
10%
Closed
1%
Open
0.6%
⚠️
673 HIGH criticality lessons
22% of classified records — each one a significant operational risk if ignored.
💡
Only 10% logged as Successes
We know what goes wrong better than what goes right. Good lesson: celebrate what works.
🎯
Data quality opportunity
580 entries (19%) have unknown criticality. Cleaning this up is a quick win in the new system.
Notes: The 78% failure rate sounds alarming but is actually normal for LL logs — people record problems, not smooth running. The 10% success rate is what we need to grow. What went right matters as much as what went wrong.

## Slide 11
11 / 19
Three Things the Data Is Telling Us
Before we look at the new system, here's what the data says about where to focus.
01
🔁
We repeat the same mistakes
Operational Issues and Mobilisation failures recur across projects spanning 15 years. Planning assumptions that fail on Project A are repeated on Project B two years later — because nobody checked.
811 Operational issues logged
02
🔕
HSE lessons are under-reported
With 1,476 lessons from Projects vs only 55 from HSEQ, there's a clear cultural gap. Safety observations, near-misses, and toolbox talk learnings rarely reach the formal log. This is a risk.
HSE = 1.8% of total database
03
💾
Knowledge leaves when people leave
With 10 separate files, no central search, and no ownership process — the database only works if someone knows it exists. Knowledge walks out the door with every staff transition.
10 disconnected source files
Notes: This slide is the pivot. We've diagnosed the problem from the data. Now we show the solution — the new IMS Lessons Learnt system.

## Slide 12
12 / 19
🚀
The New System
IMS Lessons Learnt — built into the Enshore Management System

## Slide 13
13 / 19
What Is the IMS Lessons Learnt System?
A dedicated module inside the Enshore IMS — connected to every other quality and HSE process.
1
Log It
Submit a lesson from any device — desktop, tablet or mobile — linked to a project, department, and category.
↓
2
Classify
Assign criticality (Critical / High / Medium / Low), stage/phase, and type. Required fields enforce data quality.
↓
3
Review
Line manager reviews and endorses. Notifications fire automatically — no chasing required.
↓
4
Action
Corrective or preventive actions created directly from the lesson — tracked in the Action Management module.
↓
5
Search
Any user can search, filter, and find relevant lessons before starting a project. Knowledge stays inside Enshore.
🔍
Instant Search
Full text search + multi-filter: project, dept, stage, criticality, date range
📊
Live Dashboard
KPIs, open counts, by-department and by-criticality summary — always current
📤
Export
One-click PDF report or Excel export of the filtered register
📱
Mobile Access
Log a lesson from site on your phone — no paper, no delay
🔗
Linked Actions
Actions created from lessons are tracked right to closure in the same system
📧
Auto Notifications
Email alerts to reviewers — no more chasing approvals over email
Notes: Walk through the 5-step workflow. Emphasise the link to actions — this is what turns a lesson into an improvement. The system enforces that loop.

## Slide 14
14 / 19
Before vs After
📊 Before: Excel / Shared Drive
🚀 After: Enshore IMS
Access
✗ Office only, VPN for remote
✓ Any device, anywhere, mobile-ready
Search
✗ Open all 10 files manually
✓ Instant full-text search + filters
Data quality
✗ Free-text, inconsistent fields
✓ Required fields + dropdown controls
Actions
✗ None — raised in meetings, lost
✓ Linked to Action Management module
Reporting
✗ Manual pivot tables per file
✓ Live dashboard + one-click PDF
Review process
✗ Email thread, no audit trail
✓ Structured workflow with notifications
HSE integration
✗ Separate from safety processes
✓ Connected to AINM, observations, PTW
Cross-project
✗ Impossible without opening all files
✓ Filter by any combination of fields
Notes: This is the key value proposition slide. Read down the 'After' column — every row is a pain removed. Pause on the HSE integration and cross-project rows — those are new capabilities that didn't exist at all before.

## Slide 15
15 / 19
🖥️
Live Demo
Let's open the system and explore together
1. Search for 'mobilisation' across all projects
2. Filter by High criticality + 2011–2014
3. Show the dashboard KPIs
4. Log a new lesson live
5. Show the action link
Notes: Open the browser at localhost:3000/lessons (or the live URL). Walk through the demo steps listed on the slide — they're there as a reminder, not to read aloud.

## Slide 16
16 / 19
How You Can Contribute
The database is only as good as the lessons people put in it. Here's what we need from you.
👤 Everyone
→ Log lessons as they happen — not 6 months later
→ Classify properly — check the criticality field
→ Link corrective actions before you submit
📋 Project Managers
→ Build LL reviews into project close-out
→ Share the link with clients / partners where appropriate
→ Review and endorse your team's submissions
🏢 Department Heads
→ Require LL reporting as part of mobilisation packs
→ Review open lessons at monthly team meetings
→ Call out repeat mistakes — they're in the data
⛑️ HSEQ Team
→ Use LL to feed AINM investigations
→ Connect near-misses and toolbox talks to the register
→ Build LL into audit and compliance reporting
Notes: Engagement slide. Make it clear this isn't a top-down system — the value comes from contribution. Ask if anyone has a lesson they remember right now that should go in. Usually someone does.

## Slide 17
17 / 19
What's Next
Three horizons for the Lessons Learnt system over the next 12 months.
🔧 Now — Data Quality
Clean up 580 unknown criticality records
Verify and validate the historical 10-file import
Assign owners to high-criticality lessons without actions
Complete the 2026 data entry backlog
📣 3 Months — Adoption
Lessons Learnt review embedded in every project close-out
Monthly LL report to Senior Management
Offline inspection form linked to LL submission
Client-facing export template for project reports
🧠 12 Months — Intelligence
AI-assisted search: 'find lessons relevant to this project type'
Automatic LL suggestions on new project setup
Cross-project risk pattern alerts
Lessons Learnt KPIs on the IMS Home dashboard
Notes: Be clear: the Now items are already in progress. The 3-month items need team buy-in — that starts today. The 12-month items are aspirational but grounded — we have the data foundation to support them.

## Slide 18
18 / 19
Three Asks Before You Leave
This session only matters if something changes. Here's what we're asking for.
1
✍️
Log one lesson this week
Think of a project moment that should have been captured. Go to the IMS Lessons Learnt module and log it. Takes 5 minutes. Keeps the knowledge inside Enshore.
2
📢
Tell your team the system exists
Share the link. Explain that this is now the place to log lessons — not a shared drive, not a project file. The system works when everyone contributes, not just Quality.
3
🔍
Search it before your next project kick-off
Before the next project planning meeting, spend 10 minutes searching for lessons from similar projects. Filter by vessel type, operation stage, or client. Use what's already there.
Notes: End energetically. These three asks are concrete and immediate. If people leave with one action in mind, the session has done its job. Open the floor for questions.

## Slide 19
Thank You
Questions?
The IMS Lessons Learnt system is live.
Log in at your desk and let's keep 17 years of knowledge working for us.
2,990
Lessons ready
to search
67
Projects
captured
17
Years of
intelligence
Notes: Thank the room. Remind people the system is live right now. If there's time, take 2–3 questions before wrapping up.